## Sheet1
ISC | v 1.4 06/04/2009 | Work breakdown structure
No. | Task | Subtask | External | Duration | Predecessor | Ext.dependency | Cost | Manpower | Lab | Responsible
0 | ISC management |  |  | whole project |  |  |  | 0.5 P
1 | Alignment conceptual design | [7 empty] | EGO | M. Mantovani
1.1 |  | Software identification for alignment |  | 2 weeks |  |  |  | 1 P
1.2 |  | Evaluation of Anderson vs. Ward technique |  | 2 weeks |  |  |  | 1 P
1.3 |  | MSRC: feasibility of noise evaluation due to high order modes |  | 2 weeks |  |  |  | 1 P
1.4 |  | Steady state sensing configuration (mod. freq., compatibility with quadrant freq. resp., error signals) |  | 3 months | 1.1, 1.2 |  |  | 1.5 P
1.5 |  | Steady state control configuration (radiation pressure mitigation,…) |  | 1 month | 1.1, 1.2, 1.7 |  |  | 1.5 P
1.6 |  | Noise performance (coupling to DF, electronic noise, …) |  | 1 month | 1.4, 1.5 |  |  | 1 P
1.7 |  | radiation pressure mitigation: definition of Sidles-Sigg modes for cavity with n>=3 mirrors |  | 1 month |  |  |  | 1 P
2 | Alignment design specifications | [7 empty] | EGO | M. Mantovani
2.1 |  | Beam/quadrant ports definition (noise perf., DC powers, …) |  | 1 month | 1.4, 1.5 |  |  | 1.5 P
2.2 |  | Angular accuracy specification (RMS, beam jitter, LC specs) |  | 2 months | 1.4, 1.5 |  |  | 1.5 P
3 | Alignment simulations - pre-commissioning | [7 empty] | EGO | M. Mantovani
3.1 |  | Tuning of software |  | 3 months | 1.1 |  |  | 1 P
3.2 |  | Simulation of radiation pressure in central interferometer: multiple mirror suspensions |  | 6 months | 3.1, 1.7, 1.4, 1.5 | PAY: payload model |  | 1 P
3.3 |  | Simulation of OLTF's, stability of all loops |  | 4 months | 3.1, 1.7, 1.4, 1.5 |  |  | 1 P
4 | Modulation frequencies
4.1 |  | Compatibility with EM environmental noise |  | 1 week |  |  |  | 1Ee
4.2 |  | Nominal frequency and multiple locking points?
4.3 |  | Sidebands on sidebands: possible or not? |  | 2 months |  |  |  | 1 P
4.4 |  | Definition of modulation frequencies |  | 2 weeks | 4.1, 4.3 | OSD: CITF lengths |  | 1 P
5 | Steady state locking: conceptual design
5.1 |  | Shot noise correlations and feed-forward techniques (check) |  | 6 months |  |  |  | 1 P
5.2 |  | DC locking of dark fringe: hierarchical gain, MIMO? |  | 2 weeks |  |  |  | 1 P
5.3 |  | Digital SSFS feasibility |  | 2 weeks |  |  |  | 1 P
5.5 |  | Need for 2f, 3f signals?
5.6 |  | MSRC: feasibility of noise evaluation due to high order modes
6 | Steady state locking: design specifications
6.1 |  | Radiation pressure mitigation with digital spring: parameter accuracy |  | 2 months |  |  |  | 1 P
6.2 |  | Correction filter definition |  | 2 weeks | 4.4, 6.1 |  |  | 1 P
6.3 |  | Feed-forward filters: specs at low frequency |  | 3 months |  | OSD: finesse, reflectivities |  | 1 P
6.4 |  | Feed-forward technique filter design |  | 1 month | 6.3 |  |  | 1 P
6.5 |  | Specifications on mirror control noise |  | 2 weeks | 6.2, 6.4 |  |  | 1 P
6.6 |  | Specifications on mirror control signal excursion |  | 2 weeks | 6.2, 6.4 |  |  | 1 P
6.7 |  | Specifications on RF oscillator phase and amplitude noise |  | 3 months | 6.2, 6.4 |  |  | 1 P
6.8 |  | Specifications on IMC locking accuracy |  | 3 months | 6.2, 6.4 |  |  | 1 P
6.9 |  | Specifications on IMC length noise power spectral density |  | 2 weeks | 6.2, 6.4 |  |  | 1 P
6.10 |  | Specifications on laser frequency noise |  | 2 weeks | 6.2, 6.4 | OSD: interferometer asymmetries |  | 1 P
6.11 |  | Beams & photodiodes definition |  | 2 weeks | 6.2, 6.4 |  |  | 1 P
6.12 |  | Specifications on DC powers |  | 2 weeks | 6.2, 6.4 |  |  | 1 P
6.13 |  | Specifications on sampling frequencies and delays |  | 1 week | 6.2, 6.4 |  |  | 1 P
6.14 |  | Specifications on beam quality? |  |  | 6.2, 6.4
6.15 |  | Definition of detuning |  | 1 week | 6.2, 6.4 | OSD: contrast defect |  | 1 P
6.16 |  | Specification for noise on sidebands brought by IMC |  | 3 months | 6.2, 6.4 |  |  | 1 P
7 | Steady state locking: simulations - pre-commissioning
7.1 |  | Simulation of radiation pressure (time-domain) |  | 6 months | 6.2, 6.4 |  |  | 1 P
7.2 |  | Simulation of OLTF's, stability of all loops (frequency domain) |  | 6 months | 6.2, 6.4 |  |  | 1 P
8 | Lock acquisition conceptual design
8.1 |  | Evaluation of different lock acquisition techniques |  | 3 months |  | OSD: finesse |  | 1 P | LAL | F. Cavalier
9 | Lock acquisition: design specifications
9.1 |  | Specifications on auxiliary laser frequency noise |  | 3 months | 8.1 |  |  | 1 P | LAL | F. Cavalier
9.2 |  | Auxiliary laser bench design |  | 3 months | 9.1 |  |  | 1 oE or P | LAL | F. Cavalier
9.3 |  | Purchase of lasers |  | 3 months | 9.2 |  | 100 | 0.1 oE or P | LAL | F. Cavalier
9.4 |  | Puchase of optical components |  | 3 months | 9.2 |  | 100 | 0.1 oE or P | LAL | F. Cavalier
9.5 |  | Lab tests |  | 6 months | 9.3, 9.4 |  |  | 0.5 oE + 0.5 oT | LAL | F. Cavalier
9.6 |  | Installation |  | 3 months | 9.5 |  |  | 0.5 oE + 0.5 oT | LAL | F. Cavalier
9.7 |  | Whole interferometer lock acquisition procedures |  | 2 months | 9.1, 9.2, 8.1 |  |  | 1 P
9.8 |  | Specifications on correction signal excursion |  | 2 months | 9.1, 9.2 | SUS, PAY: mirror motion |  | 1 P
9.9 |  | specification on mirror velocity nominal speed |  | 2 months | 9.1, 9.2 | SUS, PAY: mirror motion |  | 1 P
10 | Lock acquisition: simulations - pre-commissioning
10.1 |  | Lock acquisition of long arms simulation (time-domain) |  | 3 months | 9.1 |  |  | 1 P | LAL | F. Cavalier
10.2 |  | Lock acquisition of interferometer central part |  | 3 months | 9.7 |  |  | 1 P
10.3 |  | Lock acquisition of single high finesse cavity: CALVA demonstration |  |  | 9.2 |  |  |  | LAL | F. Cavalier
11 | Parametric instability mitigation conceptual design
12 | Parametric instability mitigation design specifications
13 | Parametric instabililty mitigation: simulations - pre-commissioning
Note on A1: Auteur: Subsystem abbreviation (e.g. MIR) (=Level 1 of WBS)
Note on A4: Auteur: Give a number for the task/subtask for referencing in "predecessor". 1, 1.1, 1.2 … 2, 2.1 … is probably most convenient.
Note on B4: Auteur: Task=level 2 of WBS
Note on C4: Auteur: Subtask=level 3 of WBS
Note on D4: Auteur: Enter 'E' for external orders or external work
Note on E4: Auteur: 1 week = 5 working days 1 month = 20 working days (because of holidays)
Note on F4: Auteur: Enter the number of the predecessor task or subtask. If no predecessor, enter the starting date.
Note on G4: Auteur: Give the name of any task or event outside the SS, on which this task depends.
Note on H4: Auteur: Enter the cost in k€ without tax without contingeny with all spares
Note on I4: Auteur: Give the number of persons fully employed during the task duration E.g. 1 P,0.5 eE,0.2 mT