## Sheet1
ISC | v 1.0 12/03/2008 | Work breakdown structure
No. | Task | Subtask | External | Duration | Predecessor | Ext.dependency | Cost | Manpower | Lab | Responsible
1 | Alignment conceptual design
1.1 |  | Software identification for alignment |  | 2 weeks |  |  |  | 1 P
1.2 |  | Evaluation of Anderson vs. Ward technique |  | 2 weeks |  |  |  | 1 P
1.3 |  | MSRC: feasibility of noise evaluation due to high order modes |  | 2 weeks |  |  |  | 1 P
1.4 |  | Steady state sensing configuration (mod. freq., compatibility with quadrant freq. resp., error signals) |  | 3 months |  |  |  | 1.5 P
1.5 |  | Steady state control configuration (radiation pressure mitigation,…) |  | 1 month |  |  |  | 1.5 P
1.6 |  | Noise performance (coupling to DF, electronic noise, …) |  | 1 month |  |  |  | 1 P
1.7 |  | radiation pressure mitigation: definition of Sidles-Sigg modes for cavity with n>=3 mirrors |  | 1 month |  |  |  | 1 P
2 | Alignment design specifications
2.1 |  | Beam/quadrant ports definition (noise perf., DC powers, …) |  | 1 month |  |  |  | 1.5 P
2.2 |  | Angular accuracy specification (RMS, beam jitter, LC specs) |  | 2 months |  |  |  | 1.5 P
3 | Alignment simulations - pre-commissioning
3.1 |  | Tuning of software |  | 3 months |  |  |  | 1 P
3.2 |  | Simulation of radiation pressure in central interferometer: multiple mirror suspensions (time-domain) |  | 6 months |  |  |  | 1 P
3.3 |  | Simulation of OLTF's, stability of all loops |  | 4 months |  |  |  | 1 P
4 | Modulation frequencies
4.1 |  | Compatibility with EM environmental noise
4.2 |  | Nominal frequency and multiple locking points?
4.3 |  | Sidebands on sidebands: possible or not?
5 | Steady state locking: conceptual design
5.1 |  | Shot noise correlations and feed-forward techniques
5.2 |  | DC locking of dark fringe: hierarchical gain, MIMO?
5.3 |  | Digital SSFS feasibility
5.4 |  | Optical spring in recycling cavity
5.5 |  | Need for 2f, 3f signals?
5.6 |  | MSRC: feasibility of noise evaluation due to high order modes
6 | Steady state locking: design specifications
6.1 |  | Radiation pressure mitigation with digital spring: parameter accuracy
6.2 |  | Correction filter definition
6.3 |  | Feed-forward filters: specs at low frequency
6.4 |  | Feed-forward technique filter design
6.5 |  | Specifications on mirror control noise
6.6 |  | Specifications on mirror control signal excursion
6.7 |  | Specifications on RF oscillator phase and amplitude noise
6.8 |  | Specifications on IMC locking accuracy
6.9 |  | Specifications on IMC length noise power spectral density
6.10 |  | Specifications on laser frequency noise
6.11 |  | Beams & photodiodes definition
6.12 |  | Specifications on DC powers
6.13 |  | Specifications on sampling frequencies and delays
6.14 |  | Specifications on beam quality?
6.15 |  | Definition of detuning
6.16 |  | Specification for noise on sidebands brought by IMC
7 | Steady state locking: simulations - pre-commissioning
7.1 |  | Simulation of radiation pressure (time-domain)
7.2 |  | Simulation of OLTF's, stability of all loops (frequency domain)
8 | Lock acquisition conceptual design
8.1 |  | auxiliary laser vs pulse damping vs standard locking
8.2 |  | standard locking: ringing effect and linearization evaluation
8.2 |  | standard locking: likelihood and duty cycle
8.4 |  | pulse locking: peformance evaluation
8.5 |  | auxiliary laser: reference cavity or main laser with fiber?
8.6 |  | auxiliary laser: transfer to main laser (handchecking)
8.7 |  | auxiliary laser: optical bench design
8.8 |  | auxiliary laser: time-domain software identification
9 | Lock acquisition: design specifications
9.1 |  | Specifications on auxiliary laser frequency noise
9.2 |  | Design of auxiliary laser frequency stabilization
9.3 |  | Optical scheme of auxiliary laser implementation
9.4 |  | Lock acquisition procedures
9.5 |  | Specifications on correction signal excursion
9.6 |  | specification on mirror velocity nominal speed
10 | Lock acquisition: simulations - pre-commissioning
10.1 |  | Lock acquisition of long arms simulation (time-domain)
10.2 |  | Lock acquisition of interferometer central part
10.3 |  | Lock acquisition of single high finesse cavity: CALVA demonstration
11 | Parametric instability mitigation conceptual design
12 | Parametric instability mitigation design specifications
13 | Parametric instabililty mitigation: simulations - pre-commissioning
14 | ISC management | [6 empty] | 0.2 P
Note on A1: Auteur: Subsystem abbreviation (e.g. MIR) (=Level 1 of WBS)
Note on A4: Auteur: Give a number for the task/subtask for referencing in "predecessor". 1, 1.1, 1.2 … 2, 2.1 … is probably most convenient.
Note on B4: Auteur: Task=level 2 of WBS
Note on C4: Auteur: Subtask=level 3 of WBS
Note on D4: Auteur: Enter 'E' for external orders or external work
Note on E4: Auteur: 1 week = 5 working days 1 month = 20 working days (because of holidays)
Note on F4: Auteur: Enter the number of the predecessor task or subtask. If no predecessor, enter the starting date.
Note on G4: Auteur: Give the name of any task or event outside the SS, on which this task depends.
Note on H4: Auteur: Enter the cost in k€ without tax without contingeny with all spares
Note on I4: Auteur: Give the number of persons fully employed during the task duration E.g. 1 P,0.5 eE,0.2 mT